## Avichal
Date | Member Name | Task/Activity | Status | % Complete | Hours Worked Today | Next Steps | Notes/Comments
4578600% | AAN | Developed core features of Enrollment Services module: course enrollment functionality, enrolled courses view, and course drop with validation. Integrated basic routing and tested module using run_enrollment_services.py. | Completed | 100% | 4 | Connect Enrollment with Fees & Holds and Profile modules | Implemented drop course validation logic; routing structure established and tested successfully
4578700% |  | Resolved TemplateNotFound errors by relocating templates directory to root. Integrated Bootstrap and Font Awesome into Fees & Holds UI for improved layout and clarity. Installed SQL Server and SQL Server Management Studio (SSMS), verified successful setup | Completed | 100% | 3 | setup backend logic for course enrollment | All major issues addressed. Application UI improved and backend setup completed with SQL Server and SSMS installation.

## Shivya
Date | Member Name | Task/Activity | Status | % Complete | Hours Worked Today | Next Steps | Notes/Comments
2025-05-09 | Shivya Kumar | Convert UI for login, homepage and student profile | In Progress | 90% | 8 | Continue converting UI and setting route | I was unable to run the app locally, so I created a folder named run_main_app.py with the required code Once I did that I was able to start the Flask server successfully
2025-05-10 | Shivya Kumar | Added header and footer to the remaining UIs, and converted UI for enrollment page. | In Progress | 90 | 8 | Solve my routes and fix UI | I added my routes in the same file run_main_app.py

## Yash
Date | Member Name | Task/Activity | Status | % Complete | Hours Worked Today | Next Steps | Notes/Comments

## Rohitesh
Date | Member Name | Task/Activity | Status | % Complete | Hours Worked Today | Next Steps | Notes/Comments

## Issue Register
Header | Date Raised | Raised By | Issue Description | Impact | Priority | Status | Resolution Plan | Date Resolved | Notes/Comments