## Avichal
Date | Member Name | Task/Activity | Status | % Complete | Hours Worked Today | Next Steps | Notes/Comments
4578600% | AAN | Developed core features of Enrollment Services module: course enrollment functionality, enrolled courses view, and course drop with validation. Integrated basic routing and tested module using run_enrollment_services.py. | Completed | 100% | 4 | Connect Enrollment with Fees & Holds and Profile modules | Implemented drop course validation logic; routing structure established and tested successfully
4578700% |  | Resolved TemplateNotFound errors by relocating templates directory to root. Integrated Bootstrap and Font Awesome into Fees & Holds UI for improved layout and clarity. Installed SQL Server and SQL Server Management Studio (SSMS), verified successful setup | Completed | 100 | 3 | setup backend logic for course enrollment | All major issues addressed. Application UI improved and backend setup completed with SQL Server and SSMS installation.
4578800% |  | Researched: how microservices can use different languages while being under one same system + how python will actually CRUD with SSMS( via Sqlalchemy. | Completed | 90 | 2 | complete pending ToDos
4578900% |  | Read Docker Documentation. Watched docker tutorials. Coded for course enrollment Logic | Completed | 100 | 3 | research backend logic + config | research on pulling data from firebase and pushing to sql server
4579000% |  | Resolved merge conflict and synced with main. Researched on sqlalchemy vs pyodbc. Custom validation for enrollment services. | Completed | 100 | 5 | Exception handling for all routes and research on DB | Best Wishes w/ Backend.
4579100% |  | Completed custom exception handling for all routes and custom validtion for enrollment services | Completed | 100 | 2 | Fee and Hold services routing exceptions and validations | Stay Healthy Aviiii. Don’t get sick
4579200% |  | Developed an invoice generation feature for a Flask-based enrollment system, starting with the UI in fees.html and linking it to the backend. Initially, used pdfkit to convert an HTML template to a PDF, but encountered wkhtmltopdf setup issues. To simplify, switched to ReportLab, a pure-Python library, and modified the Flask route to generate the PDF programmatically. This involved creating the PDF structure and content directly within the Python code and sending it as a download. Throughout the process, corrected routing in the HTML files to ensure proper navigation within the Flask application. | Completed | 100 | 3 | Models for Enrollment N Fees | Happy Thurday PM :)
4579300% |  | Modified invoice | Completed | 100 | 1 | Backend commencement
4579400% |  | only read docker documentation | In Progress | 10 | 1 | Port configuration
4579500% |  | configuring enrollment services to designated port | In Progress | 50 | 1 | Configure on specified port
4579600% |  | Successfully run the services on port 5004 | Completed | 100 | 1 | confgure API
4579700% |  | Backend Setup: Flask application factory pattern implemented in run_es.py. Database initialization (db.py) configured for SQLite. Flask-SQLAlchemy models (model.py) defined for all key entities from the ER diagram (Program, SubProgram, Semester, Course, CourseAvailability, Student, StudentLevel, Hold, Enrollment, CourseFee, StudentCourseFee). | In Progress | 80 | 2 | Routing and API Development:
4579800% |  | Routing and API Development: Single Flask Blueprint (enrollment_bp) established for all service routes. HTML rendering routes (/dashboard, /enroll, /display_courses, /fees, /download_invoice_pdf) implemented. Comprehensive JSON API endpoints (GET, POST, PUT, DELETE) created for all major entities. Correct url_for usage (enrollment.endpoint_name) enforced across routes.py and HTML templates. Error Resolution & Stability: jinja2.exceptions.TemplateNotFound error resolved by correct template_folder configuration and template placement. sqlalchemy.exc.AmbiguousForeignKeysError addressed in model.py by explicitly defining foreign_keys in Program and SubProgram relationships. Importance of deleting enrollment.db for schema updates highlighted and executed. Application now successfully runs and serves the dashboard and other HTML page | Completed | 100 | 4 | Database seeding (populating with initial data). Replacing mock data in frontend routes with actual database queries.

## Shivya
Date | Member Name | Task/Activity | Status | % Complete | Hours Worked Today | Next Steps | Notes/Comments
2025-05-09 | Shivya Kumar | Convert UI for login, homepage and student profile | In Progress | 90 | 8 | Continue converting UI and setting route | I was unable to run the app locally, so I created a folder named run_main_app.py with the required code Once I did that I was able to start the Flask server successfully
2025-05-10 | Shivya Kumar | Added header and footer to the remaining UIs, and converted UI for enrollment page. | In Progress | 90 | 8 | Solve my routes and fix UI | I added my routes in the same file app.py
2025-05-12 | Shivya Kumar | Customizing UI and recovered deleted codes | In Progress | 90 | 5 | Continue converting UI
2025-05-13 | shivya Kumar | Converted all user interface designs into HTML and set up respective routes. | Completed | 100 | 5 | continue implementing remaining UI logic based on feedback and custom validation with exception handling for all of her routes
2025-05-14 | Shivya Kumar | Added custom validation for logout and exception handling for all routes | Completed | 100 | 5 | Start with next workpackage once approved and given by Jayshil Singh | Not feeling well, assignments are due and short tests are approaching.
2025-05-18 | shivya Kumar | Initiated my microservice | Completed | 100 | 5 |  | Sick, too much workloads in other units
2025-05-21 | Shivya Kumar | interated jayshils feild code for student profile with mine. Added photo icon in the student profile page. Pulled jayshils code. | Completed | 100 | 8
2025-05-22 | Shivya Kumar | Integrated jayshils login code in my StudentService | Completed | 100 | 8 |  | Need 2 days time to study for cs310 PLEASEEEEEEEEEEEEEEEEEEEEE

## Yash
Date | Member Name | Task/Activity | Status | % Complete | Hours Worked Today | Next Steps | Notes/Comments
4593500% | YPP | Converted Dart files to HTML files | Completed | 100% | 4 | Updating JS to render all htmls properly | N/A
4599600% | YPP | Completed JS modification | Completed | 100% | 4 | Patch up any errors and add exception handling | N/A
13/5/2025 | YPP | Added Exception Handling | Completed | 100% | 4 | Parse XML's to registration Dropdowns | Will work on CS403 so hours worked on CS415 might decrease
14/5/2025 | YPP | Parsed XML's Properly | Completed | 100% | 5 | Waiting PM's Lead | N/A
16/5/2025 | YPP | Implemented the API Key linking | Completed | 100% | 3 | Fixing the HTML Pages and the errors that occurred due to restructuring | N/A
18/5/2025 | YPP | Implementing masterpage in all pages | Completed | 100% | 5 | Learning how to work with Docker Database | N/A
4579800% |  | Added grade recheck pages. Added students page that displays their enrollment with add and change grade and search functionalities. Added grade change and add new grade pages. | Completed | 100% | 4 | Continue docker and doing backend | Not interested

## Rohitesh
Date | Member Name | Task/Activity | Status | % Complete | Hours Worked Today | Next Steps | Notes/Comments

## Issue Register
Header | Date Raised | Raised By | Issue Description | Impact | Priority | Status | Resolution Plan | Date Resolved | Notes/Comments