## Avichal
Date | Member Name | Task/Activity | Status | % Complete | Hours Worked Today | Next Steps | Notes/Comments
4578600% | AAN | Developed core features of Enrollment Services module: course enrollment functionality, enrolled courses view, and course drop with validation. Integrated basic routing and tested module using run_enrollment_services.py. | Completed | 100% | 4 | Connect Enrollment with Fees & Holds and Profile modules | Implemented drop course validation logic; routing structure established and tested successfully
4578700% |  | Resolved TemplateNotFound errors by relocating templates directory to root. Integrated Bootstrap and Font Awesome into Fees & Holds UI for improved layout and clarity. Installed SQL Server and SQL Server Management Studio (SSMS), verified successful setup | Completed | 100 | 3 | setup backend logic for course enrollment | All major issues addressed. Application UI improved and backend setup completed with SQL Server and SSMS installation.
4578800% |  | Researched: how microservices can use different languages while being under one same system + how python will actually CRUD with SSMS( via Sqlalchemy. | Completed | 90 | 2 | complete pending ToDos
4578900% |  | Read Docker Documentation. Watched docker tutorials. Coded for course enrollment Logic | Completed | 100 | 3 | research backend logic + config | research on pulling data from firebase and pushing to sql server
4579000% |  | Resolved merge conflict and synced with main. Researched on sqlalchemy vs pyodbc. Custom validation for enrollment services. | Completed | 100 | 5 | Exception handling for all routes and research on DB | Best Wishes w/ Backend.
4579100% |  | Completed custom exception handling for all routes and custom validtion for enrollment services | Completed | 100 | 2 | Fee and Hold services routing exceptions and validations | Stay Healthy Aviiii. Don’t get sick
4579200% |  | Developed an invoice generation feature for a Flask-based enrollment system, starting with the UI in fees.html and linking it to the backend. Initially, used pdfkit to convert an HTML template to a PDF, but encountered wkhtmltopdf setup issues. To simplify, switched to ReportLab, a pure-Python library, and modified the Flask route to generate the PDF programmatically. This involved creating the PDF structure and content directly within the Python code and sending it as a download. Throughout the process, corrected routing in the HTML files to ensure proper navigation within the Flask application. | Completed | 100 | 3 | Models for Enrollment N Fees | Happy Thurday PM :)
4579300% |  | Modified invoice | Completed | 100 | 1 | Backend commencement
4579400% |  | only read docker documentation | In Progress | 10 | 1 | Port configuration
4579500% |  | configuring enrollment services to designated port | In Progress | 50 | 1 | Configure on specified port
4579600% |  | Successfully run the services on port 5004 | Completed | 100 | 1 | confgure API
4579700% |  | Backend Setup: Flask application factory pattern implemented in run_es.py. Database initialization (db.py) configured for SQLite. Flask-SQLAlchemy models (model.py) defined for all key entities from the ER diagram (Program, SubProgram, Semester, Course, CourseAvailability, Student, StudentLevel, Hold, Enrollment, CourseFee, StudentCourseFee). | In Progress | 80 | 2 | Routing and API Development:
4579800% |  | Routing and API Development: Single Flask Blueprint (enrollment_bp) established for all service routes. HTML rendering routes (/dashboard, /enroll, /display_courses, /fees, /download_invoice_pdf) implemented. Comprehensive JSON API endpoints (GET, POST, PUT, DELETE) created for all major entities. Correct url_for usage (enrollment.endpoint_name) enforced across routes.py and HTML templates. Error Resolution & Stability: jinja2.exceptions.TemplateNotFound error resolved by correct template_folder configuration and template placement. sqlalchemy.exc.AmbiguousForeignKeysError addressed in model.py by explicitly defining foreign_keys in Program and SubProgram relationships. Importance of deleting enrollment.db for schema updates highlighted and executed. Application now successfully runs and serves the dashboard and other HTML page | Completed | 100 | 4 | Database seeding (populating with initial data). Replacing mock data in frontend routes with actual database queries.
4579900% |  | fixed the Program model's primary key and adjusted relationships in model.py. The seed_db.py script was updated to ensure correct program and subprogram seeding order and linkage. Database pathing was made robust, creating necessary directories. Unicode errors were resolved by specifying UTF-8 encoding for the JSON file. Finally, data loading for all entities improved with better ID handling and fallbacks. | Completed | 100 | 3 | Link fronted with Backend
22-27 |  | Fronted to Backend Integration. Solved bugs for past 3 days and resolvement achieved today. Fully interacting with DB now: Initially, the database couldn't find tables, causing OperationalError when seeding data. The database path was misconfigured, leading to issues finding the correct enrollment.db file. A key problem was a data type mismatch, where numerical fees were treated as strings in the HTML template. The system failed when trying to format string values as numbers for display on the fees page. Handling courses without explicit fee records required ensuring numerical defaults instead of 'N/A' strings. Consistency in passing only numerical fee data to both the HTML and PDF generation functions was crucial. Finally, the invoice display was simplified by removing "Credits" and "Fee per Credit" columns, using a single "Fee" column. | Completed | 100 | 10 | enhance prereq and add new increment templates.

## Shivya
Date | Member Name | Task/Activity | Status | % Complete | Hours Worked Today | Next Steps | Notes/Comments
2025-05-09 | Shivya Kumar | Convert UI for login, homepage and student profile | In Progress | 90 | 8 | Continue converting UI and setting route | I was unable to run the app locally, so I created a folder named run_main_app.py with the required code Once I did that I was able to start the Flask server successfully
2025-05-10 | Shivya Kumar | Added header and footer to the remaining UIs, and converted UI for enrollment page. | In Progress | 90 | 8 | Solve my routes and fix UI | I added my routes in the same file app.py
2025-05-12 | Shivya Kumar | Customizing UI and recovered deleted codes | In Progress | 90 | 5 | Continue converting UI
2025-05-13 | shivya Kumar | Converted all user interface designs into HTML and set up respective routes. | Completed | 100 | 5 | continue implementing remaining UI logic based on feedback and custom validation with exception handling for all of her routes
2025-05-14 | Shivya Kumar | Added custom validation for logout and exception handling for all routes | Completed | 100 | 5 | Start with next workpackage once approved and given by Jayshil Singh | Not feeling well, assignments are due and short tests are approaching.
2025-05-18 | shivya Kumar | Initiated my microservice | Completed | 100 | 5 |  | Sick, too much workloads in other units
2025-05-21 | Shivya Kumar | interated jayshils feild code for student profile with mine. Added photo icon in the student profile page. Pulled jayshils code. | Completed | 100 | 8
2025-05-22 | Shivya Kumar | Integrated jayshils login code in my StudentService | Completed | 100 | 8 |  | Need 2 days time to study for cs310 PLEASEEEEEEEEEEEEEEEEEEEEE
2025-05-23 | Shivya Kumar | Changed the UI of the finance page from the dropdowns lists into card formats. Added copyright and contact us page | Completed | 100 | 5 |  | Need time for revision, too much work loads due to others units

## Yash
Date | Member Name | Task/Activity | Status | % Complete | Hours Worked Today | Next Steps | Notes/Comments
4593500% | YPP | Converted Dart files to HTML files | Completed | 100% | 4 | Updating JS to render all htmls properly | N/A
4599600% | YPP | Completed JS modification | Completed | 100% | 4 | Patch up any errors and add exception handling | N/A
13/5/2025 | YPP | Added Exception Handling | Completed | 100% | 4 | Parse XML's to registration Dropdowns | Will work on CS403 so hours worked on CS415 might decrease
14/5/2025 | YPP | Parsed XML's Properly | Completed | 100% | 5 | Waiting PM's Lead | N/A
16/5/2025 | YPP | Implemented the API Key linking | Completed | 100% | 3 | Fixing the HTML Pages and the errors that occurred due to restructuring | N/A
18/5/2025 | YPP | Implementing masterpage in all pages | Completed | 100% | 5 | Learning how to work with Docker Database | N/A
4579800% |  | Added grade recheck pages. Added students page that displays their enrollment with add and change grade and search functionalities. Added grade change and add new grade pages. | Completed | 100% | 4 | Continue docker and doing backend | Not interested
23/5/2025 | YPP | Implementing database for Student Registration, Changing edit Student page to display the data from database, Updating other relevant code like allSt.html | Completed | 100% | 7 | Continuing to implement the database and fixing errors | Register Students and Edit Students have been connected to the database
24/5/2025 | YPP | Finished the previous Ongoing Task | Completed | 100% | 3 | Awaiting Avichals End of Enrollment and Holds to integrate the new functionalities | N/A

## Rohitesh
Date | Member Name | Task/Activity | Status | % Complete | Hours Worked Today | Next Steps | Notes/Comments

## Issue Register
Header | Date Raised | Raised By | Issue Description | Impact | Priority | Status | Resolution Plan | Date Resolved | Notes/Comments